Community Health Improvement Plan FY26-28

Action Plan with Updates

Date of Update: 4/8/26 (for updates Jan-Mar. 2026)

(Note SHIP and CHNA alignment)

Priority: Healthy Beginnings Healthy lifestyle activities related to prevention and care for maternal, infant, and family health. Workgroup: Growing Health Families (GHF) Workgroup Co-Chairs: Samantha Cribbs, RN; Erica Taylor, MS LHIC Staff: Stephanie Foster Alignment: Aligns with Maryland SHIP Priority Area 3 Women’s Health, Goal 1 Improve maternal health outcomes through improved maternal care before, during and after pregnancy. CHNA 2022: Healthy Beginnings. Key Measures: - Infant Mortality: - Rate: 4.7 infant deaths per 1000 live births overall in 2022, 3-yr rate - Disparity: 6.7 per 1000 live births in Blacks in 2022, 3-yr rate - SHIP target: 5.2 for Maryland overall by 2029 - Low Birthweight Births: - Rate: 9.2% of live births overall in 2022 - Disparity: 13.1 % of live births in Blacks in 2022 - SHIP target: 8.7% for Maryland overall by 2029 - Maternal Deaths: - Rate: 36.2 pregnancy-related deaths per 100,000 live births overall in 2022, 5-yr rate - Disparity: 60% of the 10 maternal deaths between 2010 and 2022 were Black women - SHIP target: 17.2 or fewer pregnancy-related deaths per 100,000 live births overall for Maryland by 2029

Goal 1. Improve health outcomes for Black/African American infants and mothers through improved maternal care before, during and after pregnancy.

Objective 1.1. By June 2028, increase awareness of educational and other resources available to Black/African-American mothers and infants in Howard County.

Measure: Baseline: 1 annual BMHW events Target: 3 BMHW events (1 per year)

Time Frame: July 2025 – June 2028

Lead Person: Stephanie Foster

Action Steps: - Collaborate with members of the Growing Healthy Families Workgroup to coordinate a Black Maternal Health Week Event in April 2026, 2027, and 2028. - Promote culturally sensitive and accessible education programs for Black mothers on prenatal and postnatal care, healthy nutrition, and recognizing warning signs of complications during pregnancy. - Create culturally relevant and accessible materials and use community leaders to disseminate information about doulas and their value during pregnancy and childbirth.

Status Comment and Date of Review: - 10/7/25 Update: - Planning for the 2026 Black Maternal Health Week Event will start later in the month of October 2025. - 12/12/25 Update: - 2026 Black Maternal Health Week Event is scheduled for April 18, 2026, at the Harriet Tubman Cultural Center. - 4/1/26 Update: - 2026 Black Maternal Health Week Event will include workshops and sessions focused on healthy nutrition for families, self-guided journaling, and meditation activities.

Objective 1.2. By June 2028, increase awareness of doula services as a potential alternative or in conjunction with traditional hospital care.

Measure: Baseline: 1 resource about Doulas, pre- and postpartum Target: 2 resources about Doulas, pre- and postpartum

Time Frame: July 2025 – June 2028

Lead Person: Stephanie Foster

Action Steps: - Promote the use of doulas, the HCHD Perinatal Equity and Care for Everyone (P.E.A.C.E.) program, community health centers and resources in Howard County Community Schools. - Collaborate with Community Health Centers to promote culturally appropriate high-quality care for Black/African American mothers and infants. - Create a video project with community members on the benefits of doulas. Increase awareness of resources in Howard County Community Schools. - Disseminate culturally relevant and accessible information about the value of doulas.

Status Comment and Date of Review: - 10/9/25 Update: - Promoted the launch of the Howard County Health Departments Doula Partnership Program aimed at improving maternal and infant health by bridging public health services with private-sector expertise. - Promoted the Howard County Health Departments Doula Training which provided interested community residents with doula training and mentorship opportunities, including a scholarship to support and serve families in Howard County - Shared information about HCHD October 2025 Diaper Giveaways and Doula, Dads Breastfeeding events, and P.E.A.C.E. Project materials at the 2025 Oakland Mills Fall Festival. - 4/1/26 Update: - Continued promotion of the Howard County Health Department Doula and the Perinatal Equity and Care for Everyone (P.E.A.C.E.) Project services.

Goal 2. Enhance equitable access to healthcare by expanding awareness of affordable health coverage, community health services, and transportation assistance, while also improving opportunities for prenatal care and nutrition education for all women in Howard County.

Objective 2.1. By June 2028, collaborate with the Growing Healthy Families workgroup members to increase awareness of affordable healthcare coverage, availability of community health centers, and information about transportation assistance to health care facilities.

Measure: Baseline: 0 awareness opportunity Target: 1 awareness opportunity

Time Frame: July 2025 – June 2028

Lead Person: Stephanie Foster

Action Steps: - Disseminate culturally appropriate and accessible community support programs, advocate for policy changes, and collaborate with local organizations to address social and environmental factors affecting health. - Strengthen partnerships with community-based organizations to enhance access to and awareness of affordable healthcare, prenatal care, and maternal health support by sharing culturally appropriate and accessible resources for new mothers. - Improve awareness of the culturally appropriate and accessible resources available in the county through CAREAPP. - Develop dissemination efforts highlighting access to mental health screenings, offer culturally sensitive counseling services, and create support groups for mothers experiencing stress and anxiety (i.e., National Maternal Mental Health Hotline). - Explore themes related to women’s health issues including ways to improve access to care through collaborative focus groups. - Expand partnerships with faith-based organizations to increase awareness of programs and events for prenatal care.

Status Comment and Date of Review: - 12/12/25 Update – Meet with Pastor Hyiwot Teshome of St. John United Methodist Church about becoming a member of HCLHIC.

Objective 2.2. By June 2028, collaborate with workgroup members to increase opportunities to access affordable prenatal care and nutrition education for all women.

Measure: Baseline: 0 partnership Target: 1 partnership

Time Frame: July 2025 – June 2028

Lead Person: Stephanie Foster

Action Steps - Collaborate with the Women, Infants, and Children (WIC) Program and similar organizations to promote culturally appropriate and accessible prenatal care and healthy eating, and nutrition resources for all women. - Strengthen collaboration between healthcare providers, nutrition experts, and faith-based organizations to ensure seamless access to support services for maternal health.

Status Comment and Date of Review:

Goal 3. Engage community members in women and maternal health activities by increasing awareness of culturally appropriate and inclusive opportunities to improve access to healthcare.

Objective 3.1. By June 2028, enhance awareness, access to affordable healthcare and well-being for all women in Howard County by creating tools to support women in the community.

Measure: Baseline: 0 awareness opportunity Target: 1 awareness opportunity

Time Frame: July 2025 – June 2028

Lead Person: Stephanie Foster

Action Steps - Explore themes related to women’s health issues through focus groups. - Create and promote a culturally appropriate, accessible, and inclusive toolkit to guide advocacy efforts related to improved access to healthcare for women in Howard County. - Collaborate with other HCLHIC workgroups to promote physical and mental health among women in Howard County. - Promote culturally appropriate, accessible, and inclusive resources for mothers with multiple births (twins, triplets), fathers and grandparents. - Foster collaborative partnerships with community-based organizations to promote culturally appropriate, accessible, and inclusive resources for women.

Objective 3.2. By June 2028, expand engagement opportunities to improve physical and mental health and social engagement among all women in the community.

Measure: Baseline: 0 engagement opportunities Target: 1 engagement opportunity

Time Frame: July 2025 – June 2028

Lead Person: Stephanie Foster

Action Steps - Incorporate mental and physical messaging during Black Maternal Health Week. - Create engagement opportunities related to mental health for women in collaboration with Growing Healthy Families and Healthy Minds and Suicide Prevention workgroups. - Foster collaborative partnerships with community-based organizations to promote culturally appropriate and accessible resources to improve health outcomes for pregnant women. - Collaborate and promote culturally appropriate and accessible resources from providers offering alternative therapy (e.g. music and animal therapy). - Collaborate with healthcare organizations, faith-based organizations, schools, and community-based organizations to promote culturally appropriate and accessible mental health resources for mothers experiencing stress and anxiety.

Status Comment and Date of Review: - 9/24/25 updates: Howard County Local Health Improvement Coalition and the Bureau of Family Health Services will conduct Women’s Health Focus Groups (WHFG) on the following dates: - November 5, 2025, 12:30-2:00 pm (Family Support Center) - December 3, 2025, 6:00 – 7:30 pm (Virtual Only via Zoom) - January 10, 2026, 10:00 – 11:30 am (in-person at Harriet Tubman Cultural Center with a virtual backup) - 12/12/25 update: Will provide handouts to attendees of the January 10, 2026, WHFG session about the 2026 Black Maternal Health Week Event on April 18, 2026. - 4/1/26 update: Feedback will be collected from attendees of the 2026 Black Maternal Health Week event to assess interest in hosting an additional Women’s Health Focus Group session. - Pending sufficient interest, the next Women’s Health Focus Group is tentatively planned for June 2026.

Priority: Healthy Living Healthy lifestyle activities for disease prevention through improved access to healthy foods, health education, safe physical activity opportunities, and healthcare. Workgroup: Healthy Lifestyle Workgroup (Physical Activity + Chronic Disease Prevention + Access to Healthy Food) Co-Chairs: Michelle Rosenfeld; Carrie Ross LHIC Staff: Maribet Rivera-Brute, MPH Alignment: Aligns with Maryland SHIP Priority 1 Chronic Disease Goal 1: Enhance primary prevention of chronic disease Priority 1 Goal 2 Enhance screening, treatment and care for chronic illness CHNA 2022: Healthy Living. Key Measures: - Overweight and Obesity: - Prevalence: 59.8% of adults are overweight or obese in 2022 - Disparity: 68.3% of Black adults are overweight or obese in 2022 - Obesity in High School Students - Prevalence: 9.7% of high school students were obese overall in 2022 - Disparity: 12.4% of Black and 21.7% of Hispanic high school students were obese in 2022 - Physical Activity - Prevalence: 44% of high school students report physical activity at least five days a week in 2022 - Food Insecurity - Prevalence: 9.7% reported food insecurity overall in 2022 - Disparity: 18% of Black and 12% of Hispanic people reported food insecurity in 2022 - SHIP target: 8.3% reporting food insecurity by 2029 - Diabetes - Prevalence: 12% overall in 2024; Gestational diabetes at 11% in 2021 - Disparity: Hospital readmission rates 19% overall, 22% in Blacks in 2023 - Hypertension: - Prevalence: 28% overall in 2021 - Disparity: 34.5% in Blacks in 2021 - SHIP target: 18.9% overall in Maryland by 2029 - Fall-related deaths: - Rate: 10.2 per 100,000 in 2022, 3-yr rate, increased from 9.3 in prior period

Goal 1. Advance healthy lifestyle behaviors through culturally responsive, inclusive, and accessible communication strategies that promote nutrition education, physical activity, safe pedestrian environments, and equitable access to health services, with a focused commitment to reaching and uplifting the most vulnerable community members.

Objective 1.1. By June 2028, collaborate with the HCHD and partners to implement and evaluate healthy lifestyle messages for priority populations to improve health outcomes.

Measure: Baseline: 5 dissemination efforts Target: 5 dissemination efforts

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps - Plan, implement, and evaluate population-specific culturally appropriate, accessible and inclusive healthy lifestyle social media messaging. - June 2026 - April 2026: Plan healthy lifestyle social media dissemination efforts. - April 2026 – August 2027: Launch healthy lifestyle social media dissemination efforts. - Track social media engagement for digital dissemination efforts. - Track click through rates for digital dissemination efforts (Howard County/HCHD website metrics). - Promote healthy positive behavior graphics through social media, newsletters, HCHD and partner communications, as well as through CHWs. - May 2026 - August 2027: Utilize Community Health Workers (CHWs) to work on specific zip codes areas with tailored messaging. - Collaboration with Howard County Transportation to disseminate culturally sensitive and accessible messages about safe walking along streets. - Collaboration with Howard County Transportation utilizing CHWs to enhance their High Injury Network. - August 2027– June 2028: Evaluate Healthy Lifestyle Dissemination Efforts - Advocate for changes to the built environment as needed to increase opportunities for safe walking along streets. - Engage faith-based organizations to integrate health messaging into community programs or outreach events. - Create short, engaging videos, and infographics on nutrition, preventive care, and available health services.

Status Comment and Date of Review: July – September 2025 - 9/24/25 update- Begin SNAP/Diabetes Communication Campaign on social media and through the Community Assets Profile (CAP) project as dissemination efforts. - 10/6/25 update- Healthy Lifestyle workgroup members partnered with the HCLHIC to increase dissemination efforts: - Maryland Hunger Solutions - Howard County Public School System (HCPSS) - African Immigrants Dream, Inc. - Howard County Office of Aging and Independence (OAI) - Johns Hopkins Howard County Medical Center (JHHCMC) - Howard County Regional Transportation Agency (RTA)

Objective 1.2. By June 2028, establish strategic partnerships with local healthcare providers, faith-based organizations, and businesses to collaboratively develop and distribute health education materials to promote chronic disease prevention and nutrition-focused wellness.

Measure: Baseline: 0 partnerships Target: 3 partnerships

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps: - Collaborate with businesses and local healthcare organizations to display culturally appropriate, accessible, and inclusive health information in their organizations. - Promote interactive nutrition education workshops in collaboration with healthcare and community-based organizations to encourage healthy eating. - Update and disseminate Food Assistance and Nutrition Education Program Guide on a bi-annual basis.

Status Comment and Date of Review: July – September 2025 - 10/6/25 updates: - Began Partnership with Pastor Hyiwot from St. John United Church - Began Partnership with Pastor Mitch from CrossLife Church - Strengthened partnership with Maryland Hunger Solutions - Will disseminate SNAP/Diabetes Communications campaign materials to clients - Strengthened partnership with Howard County Public School System - Will disseminate SNAP/Diabetes Communications campaign materials to schools

Objective 1.3. By June 2028, enhance community awareness of health education opportunities by improving access to tailored health information and essential health services through strategic outreach and engagement initiatives.

Measure: Baseline: 0 education opportunity/partnership Target: 1 education opportunity/partnership

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps - Collaborate with community partners and members to raise awareness and encourage use of health services. - Partner with faith-based organizations, schools, and local businesses to disseminate health information where community members gather. - Partner with healthcare organizations to distribute culturally sensitive, accessible, and inclusive educational materials in waiting rooms. - Include QR codes and plain language in health education materials to improve accessibility. - Promote the use of CAREAPP to increase nutrition education, chronic disease prevention and other health education resources.

Status Comment and Date of Review: July – September 2025 - 10/6/25 Updates: - Attended Howard County Falls Prevention Retreat with other organizations focused on falls prevention on June 10, 2025 - Attended Fall Prevention Week Kick Off – Open House with OAI and LHIC (Enterprise Partnership) in August 2025 - Provided awareness of health education opportunities to 18 and older adult residents - Provided Resources at Parkview at Ellicott City Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 40 older adult residents - Provided Resources at Sierra Woods Apartments Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 25 older adult residents - Educated Residents on HCLHIC and HCHD resources and services and signed up interested residents for walking groups at Parkview Ellicott City - Strengthened partnership with Enterprise - Educated Residents on HCLHIC and HCHD resources and services and signed up interested residents for walking groups at Parkview Snowden River - Strengthened partnership with Enterprise - Educated Residents on HCLHIC and HCHD resources and services and signed up interested residents for walking groups at Parkview Columbia - Strengthened partnership with Enterprise October – December 2025 - Continued partnership with Enterprise residential communities

Objective 1.4. By June 2028, enhance physical activity and pedestrian safety among youth in Howard County by integrating health education initiatives with community-supported programs.

Measure: Baseline: 0 education opportunity/partnership Target: 1 education opportunity/partnership

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps - Collaborate with Howard County Department of Transportation to promote “walk to work” or “walking school bus” activities and share culturally appropriate, accessible, and inclusive resources to encourage safe pedestrian movement and physical activity. - Collaborate with schools and community organizations to create health education opportunities for youth to encourage physical activity.

Status Comment and Date of Review: July – September 2025 - 10/6/25 Update: Met with Ducketts Lane Elementary School to provide planning support and resources for their “Ruby Bridges” Walk to School event in November 2025

Objective 1.5. By June 2028, to collaborate with community partners to continue physical activity initiatives to encourage Howard County community members of all ages and abilities to engage in movement for improved physical and mental health.

Measure: Baseline: 0 educational opportunity Target: 2 educational opportunities

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps: - Convene Healthy Lifestyle workgroup partner meetings to plan, implement and evaluate annual Walktober and WalkMDDay collaborative movement events and activities in October - Engage diverse community partners to promote Walktober initiatives and share culturally appropriate, accessible, and inclusive resources to encourage physical activity - Widely promote Walktober calendar of events and other State-led and Walktober events - Evaluate Walktober efforts to improve in subsequent years - Present results to partners in Healthy Lifestyle meeting - Create and promote walking groups in neighborhoods, especially in senior communities, to encourage people to be more active and connect with others - Disseminate walking group opportunities through Member Resources and monthly digests

Status Comment and Date of Review: - 10/6/25 updates: - Started Walktober 2025 with 170 events - Walktober and Falls Prevention Awareness Week planning meetings with Healthy Lifestyle workgroup members started in July 2025 - Started Walking Group at Legacy at Twin Rivers (Columbia) (Enterprise Partnership) in July 2025 - Provided awareness of health education opportunities to 30 mixed age residents - Started Walking Group at Parkview at Ellicott City (Ellicott City) (Enterprise Partnership) in September 2025 - Provided awareness of health education opportunities to 50 older adults residents (across 3 events) - Started Walking Group at Parkview Snowden River (Enterprise Partnership) in September 2025 - Provided awareness of health education opportunities to 17 residents - Started Walking Group at Parkview Columbia (Enterprise Partnership) in September 2025 - Provided awareness of health education opportunities to 8 older adult residents - 11/5/2025 - Finished Walktober 2025 with 171 events, with estimated 4,400 participants across Howard County - HCHD Walktober Challenge finished with 5,082,085 steps or 2,310.04 miles walked in total - Collaborated with Howard County Village Leaders for the Howard County Village 2025 Walktober Challenge (Original collaboration began August 20, 2025) - 5 Howard County Villages joined in the Howard County Village 2025 Walktober Challenge - 41 participants with 4,009.50 miles walked in October; Wilde Lake Village winner for 2025 with 18 participants walking 1,672.94 miles in October - 1 village expressed interest to join next year - Community members expressed interest in competing again next year

Goal 2. Continue raising awareness of culturally appropriate, accessible, affordable, and nutritious food to decrease food and nutrition insecurity among Howard County residents.

Objective 2.1. By June 2028, increase awareness of and access to culturally appropriate, accessible, affordable, and nutritious food for Howard County residents across the lifespan.

Measure: Baseline: 0 dissemination opportunity Target: 2 dissemination opportunities

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps: - Provide awareness of food and meal sites provided by community partners through the Food Connections Map. - Update and disseminate Food Pantry and Hot Meals brochures on a bi-annual basis. - Continue creating food pantry spotlight videos to highlight the work of HCLHIC’s community partners as an effort to reduce food insecurity. - Continue supporting container gardens at senior residential communities through the involvement of HCLHIC’s community partners. - Support community partners’ efforts to improve school menu options.

Status Comment and Date of Review: July – September 2025 - 10/6/25 updates: - Completed Owen Brown and Parkview Columbia Seedling Delivery - Food Pantry Brochures and Food Map Posters remain updated - Provided Resources at Parkview at Ellicott City Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 40 older adult residents - Provided Resources at Sierra Woods Apartments Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 25 older adult residents - Provided Resources at Parkview Ellicott City Fall Prevention Kick-off (Enterprise Partnership) - Provided awareness of health education opportunities to 10 older adult residents - Provided Resources at Parkview at Snowden River - Provided awareness of health education opportunities to 18 older adult residents - Provided Resources at Parkview at Columbia - Provided awareness of health education opportunities to 8 older adult residents January – March 2026 updates - Updated Food Connections Map and food pantry brochures

Objective 2.2. By June 2028, partner with local communities, schools, healthcare organizations, and faith-based organizations to promote food resources.

Measure: Baseline: 0 partnership Target: 3 partnerships

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps: - Promote culturally appropriate, accessible and inclusive educational materials on healthy eating and food access tailored to diverse populations and languages. - Identify individuals at risk for food insecurity through the CAREAPP Needs Assessment and refer them to culturally appropriate and accessible food resources. - Collaborate with faith-based organizations to increase awareness of food distribution sites and promote culturally appropriate food resources at places of worship. - Collaborate with local communities, faith-based organizations, and schools to provide nutritional education.

Status Comment and Date of Review: July – September 2025 - 10/6/25 Updates: - Began Partnership with Pastor Hyiwot from St. John United Church - Began Partnership with Pastor Mitch from CrossLife Church - Provided Resources at Parkview at Ellicott City Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 40 older adult residents - Provided Resources at Sierra Woods Apartments Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 25 older adult residents - Provided Resources at Parkview Ellicott City Fall Prevention Kick Off (Enterprise Partnership) - Provided awareness of health education opportunities to 10 older adult residents - Provided Resources at Parkview Snowden River (Enterprise Partnership) - Provided awareness of health education opportunities to 17 older adult residents - Provided Resources at Parkview Columbia (Enterprise Partnership) - Provided awareness of health education opportunities to 8 older adult residents October-December 2025 - 12/31/2025 Updates: - Partnered with Sherwood Crossings in Elkridge to share information about the food pantries and hot meals with new and current residents

Goal 3. Increase awareness of fall risk and opportunities to promote culturally appropriate and accessible resources to decrease falls among community members.

Objective 3.1. By June 2028, collaborate with community-based organizations and residential communities to promote culturally appropriate and accessible falls prevention resources and activities.

Measure: Baseline: 0 fall prevention initiative Target: 1 fall prevention initiative

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps: - Collaborate with organizations to promote culturally appropriate, accessible, and inclusive resources to reduce falls risk during Falls Prevention Week and year-round. - Collaborate with organizations such as the Howard County Office on Aging and Independence (OAI), Howard County Fire and Rescue and JHHCMC to promote movement and strength training among community members year-round, such as walking groups

Status Comment and Date of Review: July – September 2025 - 10/6/25 updates: - Attended Howard County Falls Prevention Retreat with other organizations focused on falls prevention on June 10, 2025. - Participated in Fall Prevention Week Kick Off – Open House with OAI and LHIC (Enterprise Partnership) - Provided awareness of health education opportunities to 18 older adult residents - Provided Resources at Parkview at Ellicott City Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 40 older adult residents - Provided Resources at Parkview Ellicott City Fall Prevention Kick off (Enterprise Partnership) - Provided awareness of health education opportunities to 10 older adult residents - Provided Resources at Sierra Woods Apartments Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 25 older adult residents

Objective 3.2. By June 2028, create educational opportunities to increase knowledge about fall risk factors and preventative measures.

Measure: Baseline: 0 educational opportunity Target: 1 educational opportunity

Time Frame: July 2025 – June 2028

Lead Person: Maribet Rivera-Brute

Action Steps: - Create short videos promoting movement to increase physical activity among community members across the lifespan. - Disseminate free and low-cost physical activity and falls prevention programs using CAREAPP. - Partner with community-based organizations, healthcare providers and subject matter experts to promote educational events to increase awareness of risks in the home to prevent falls.

Status Comment and Date of Review: October-December 2025 - 10/6/25 Update: - Attended Fall Prevention Week Kick Off – Open House with OAI and LHIC (Enterprise Partnership) in August 2025 - Provided awareness of health education opportunities to 18 and older adult residents - Provided Resources at Parkview at Ellicott City Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 40 older adult residents - Provided Resources at Sierra Woods Apartments Resource Fair (Enterprise Partnership) - Provided awareness of health education opportunities to 25 older adult residents - Educated Residents on HCLHIC and HCHD resources and services and signed up interested residents for walking groups at Parkview Ellicott City - Strengthened partnership with Enterprise - Educated Residents on HCLHIC and HCHD resources and services and signed up interested residents for walking groups at Parkview Snowden River in September 2025 - Strengthened partnership with Enterprise - Educated Residents on HCLHIC and HCHD resources and services and signed up interested residents for walking groups at Parkview Columbia in September 2025 - Strengthened partnership with Enterprise

Priority: Healthy Minds Health promotion for social engagement to support mental wellness and behavioral health. Workgroup: Healthy Minds and Suicide Prevention Coalition (HMSPC) Co-Chairs: Barbara Allen; Jessica Fisher, LCSW-C LHIC Staff: Stephanie Foster Alignment: Aligns with Maryland SHIP Priority 4 Goal 1: Reduce firearm-related suicides, homicides, and injuries SHIP Priority 5 Goal 1: Expand access to, and utilization of, behavioral health services SHIP Priority 5 Goal 2: Reduce disparities in mental health outcomes CHNA 2022: Healthy Minds. Key Measures: - Depression, Hopelessness: - Rate: 16.5% of adults reported a depression diagnosis in 2022, increased from 14.2% in 2016 - Disparity: 32% of youth overall reported hopelessness in 2022, compared with 44% in females, 41% in Hispanics, and 34% in Blacks. - SHIP target: Reduce percentage of students feeling hopeless from 42% overall in Maryland - Suicide: - Rate: 16% of youth considered suicide in 2022, increased from 14% in 2013 - Disparities: 21% females, 19% Hispanics, 16% Black youth considered suicide in 2022. Of the 28 youth (10-19 yr old) suicides between 2013-2022, 46% were non-Hispanic white, 36% non-Hispanic Black. Suicide readmission rates for Blacks (18%) were higher than overall (13%) in 2024, but all other mental health admissions are much lower for Blacks (6%) than overall (21%), 2023. - Firearm assault deaths: - Rate: Yearly average of 6 (2015-2018) increased to 14 (2019-2022) - Disparity: 92% male, 83% Black in 2022

Goal 1. Promote safe home practices such as safe storage of medications, firearms, and other harmful materials, and reduce stigma of mental health support through education and community engagement.

Objective 1.1. By June 2028, collaborate with workgroup members to create and promote culturally appropriate, accessible and inclusive materials to make homes safer to prevent suicide.

Measure: Baseline: 0 collaboration Target: 3 collaborations

Time Frame: June 2026 – December 2028

Lead Persons: Stephanie Foster, Jessica Fisher, Barbara Allen

Action Steps - Promote the Safeguard your Home brochure to increase awareness of strategies to make homes safer. - Create and promote an online toolkit to increase awareness of suicide prevention strategies with checklists, action steps and infographics. - Collaborate with community centers, healthcare organizations, community-based organizations and local businesses to disseminate educational materials among community members.

Status Comment and Date of Review: January – March 2026 - Started collaboration with Mercy Health Services to share the Safeguard your Home brochures.

Objective 1.2 By June 2028, increase community engagement to support mental health among priority populations through local partnerships and peer support programs.

Measure: Baseline: 0 update Target: Quarterly Update

Time Frame: June 2025 – December 2028

Lead Persons: Stephanie Foster, Jessica Fisher, Barbara Allen

Action Steps - Review HCLHIC website Healthy Minds pages and make updates as needed quarterly - Increase awareness of culturally competent mental health providers in Black/African-American communities - Promote the HCLHIC website, Howard County Behavioral Health resources and Mental Health and Suicide Prevention Programs and other local and national behavioral health resources widely - Launch awareness initiatives within the Howard County Public School System to de-stigmatize mental health issues and encourage young people to seek help. - Promote culturally appropriate, accessible, and inclusive social engagement opportunities and resources for those with substance use and mental health disorders. - Create a community outreach initiative (involving BBH and HMSPC Workgroup members) to promote Safe Storage Locks, Boxes and Safeguard Your Home Brochure.

Status Comment and Date of Review:

Goal 2. Develop initiatives highlighting community violence intervention programs, promoting safe firearm storage and ownership practices, and collaborating with law enforcement agencies to address illegal firearms and reduce gun violence.

Objective 2.1. By June 2028, support community-based initiatives to reduce firearm-related deaths among priority populations in Howard County.

Measure: Baseline: 0 initiative Target: 1 initiative

Time Frame: July 2025 – June 2028

Lead Persons: Stephanie Foster, Jessica Fisher, Barbara Allen

Action Steps - Collaborate with workgroup members on outreach programs to educate the community on firearm safety and violence prevention. - Promote safe firearm storage practices and access to free gun storage devices/options. - Collaborate with the school system on community-based violence intervention campaigns that provide alternatives to violence for at-risk individuals.

Status Comment and Date of Review: - 10/6/25 Updates: - HCHD hosted a press event on June 26, 2025, at the Elkridge Branch Library, to announce a community initiative that provides free gun locks to residents in an effort to prevent firearm-related suicides. This initiative is a collaboration between the Health Department (HCLHIC and BBH), Howard County Library System, Howard County Police Department, and the VA Maryland Health Care System. - The Gun Lock Giveaway Program will be held at two county library branches (Elkridge and East Columbia). This initiative is primarily aimed at safe firearm storage to help prevent suicides and other firearm-related tragedies. A total of 350 locks given since June 26th. 382 were given as of week ending on July 25th. - Began a partnership with Tactical 52, LLC, a veteran-owned organization dedicated to firearm safety education, training, and responsible ownership. - The discussion about creating a Firearms Safe Storage Workshop began to promote the safe handling of firearms, safe storage practices, and community safety initiatives, to help with our initiative in reducing firearm-related injury and deaths. - 12/12/25 Updates: - Partnered with Tactical 52, LLC (Ken Abrams) to host the Firearms Safe Storage Workshop. Date and time to be determined. - Coordinating with Jen Pauliukonis, Executive Director of the Maryland Department of Health’s Center for Firearm Violence Prevention and Intervention, to give a presentation at the Firearm Safe Storage Workshop. - 4/1/26 Update: - The Firearm Safe Storage Workshop was held on March 14, 2026, at the Historic Oakland Manor from 11:00 AM – 12:30 PM. - 25 people registered for the event. 20 people attended. - Jen Pauliukonis, Executive Director of the Maryland Department of Health’s Center for Firearm Violence Prevention and Intervention, presented statewide data trends related to firearm-related suicide deaths in Maryland. - Jessica Fisher, Suicide Prevention Coordinator for the Bureau of Behavioral Health at the Howard County Health Department, served as the workshop moderator. She also provided context for the workshop and shared data on firearm-related suicide deaths in Howard County. - Ken Abrams and Rodney Young of Tactical 52 presented the best practices for safe firearm storage, demonstrated various types of gun locks available to community members, and provided an overview of relevant Maryland firearm laws. - Members of Be SMART and the American Foundation for Suicide Prevention (AFSP) attended the workshop to provide valuable information and resources to attendees. - A raffle was held to give one of the attendees of the workshop a biometric gun lockbox.

Objective 2.2. By June 2028, expand partnerships with local organizations, schools, and law enforcement agencies to provide support and address the unique mental health needs of priority populations in Howard County.

Measure: Baseline: 0 partnership Target: 2 partnerships

Time Frame: July 2025 – June 2028

Lead Persons: Stephanie Foster, Jessica Fisher, Barbara Allen

Action Steps - Collaborate with Howard County Police and other law enforcement agencies to increase resource accessibility and promote prevention initiatives through joint efforts. - Identify and collaborate with Black/African American-led community-based organizations already working on mental health initiatives. - Collaborate with schools to create a virtual event for parents and students to increase awareness of mental health early intervention.

Status Comment and Date of Review: - 10/6/25 Updates: - Engaged with Howard County Health Department (HCHD) Community Engagement Division and shared the Safeguard Your Home Brochure with members of the division in the effort of promoting suicide prevention initiatives. - Partnered with Africans for Mental Health and Everstand Behavioral Health to help promote their organizations Mental Health First Aid courses for adults and youth and the Question, Persuade, and Refer (QPR) Suicide Prevention Training. - 12/12/25 Updates: - Partnered with Everstand Behavioral Health to help promote their organization Mental First Aid courses for youth. - Contacted Stepping Towards A New Destiny (S.T.A.N.D.) to provide presentations at the July Full LHIC meeting and the Healthy Minds & Suicide Prevention Coalition (HMSPC) Workgroup meeting regarding their work with African American youth in the community. - 4/1/26 Updates: - The Horizon Foundation and the American Foundation for Suicide Prevention (AFSP) gave presentations during the March 12th HMSPC Workgroup meeting which provided information of various MD legislative bills related to mental health that are being worked and voted in the state of Maryland. - Shared information about the March 14th Firearm Safe Storage Workshop to Howard County Police Officers Jeremy Zhou and Brian Baer.

Goal 3. Promote culturally appropriate and accessible mental health and behavioral resources through partnerships with local organizations and businesses serving priority populations.

Objective 3.1. By June 2028, collaborate with organizations and social groups hosting mentorship programs to promote culturally appropriate, accessible and inclusive mental health resources.

Measure: Baseline: 0 partnership/collaboration Target: 1 partnership/collaboration with one educational opportunity

Time Frame: July 2026 – June 2028

Lead Persons: Stephanie Foster, Jessica Fisher, Barbara Allen

Action Steps - Promote culturally appropriate, accessible, and inclusive mental health resources through outreach events and collaboration with partner agencies including schools, community-based organizations, and faith-based organizations. - Promote culturally appropriate, accessible and inclusive Substance Use and mental health resources widely via CAREAPP, HCLHIC website, and workgroup members. - Expand awareness and access to culturally appropriate, accessible and inclusive mental health and social support resources, with an emphasis on peer mentorship for adults and youth. - Disseminate culturally responsive mental health training resources from community partners and national organizations to enhance healthcare providers’ knowledge to offer culturally appropriate and equitable mental health care.

Status Comment and Date of Review: - 4/1/26: Attended Voices of Faith, Journeys of Healing: A Discussion on Mental Health, which explored the barriers and challenges individuals within faith communities face when experiencing mental health challenges, particularly within church settings. - Pastor Hyiwot Teshome of St. John United Methodist Church was one of the speakers and announced the development of the Congregational Depression Awareness Program (CDAP). This initiative will offer training for individuals to become certified CDAP facilitators, enabling them to deliver mental health awareness workshops within their churches twice annually. - Shared the Safeguard Your Home brochures, the Food Connection Map, and food pantry brochures with Center Park Pharmacy to support community access to safety and nutrition resources. - Connected the Crosswalk Lutheran Church with the Grassroots Crisis Intervention Center’s Director of Marketing (Laura Crovo) so that Crosswalk can meet to discuss the resources the center provides to residents in the community.

Objective 3.2. By June 2028, collaborate with organizations and social groups providing resources for community members seeking help to improve behavioral health priority populations.

Measure: Baseline: 0 partnership/collaboration Target: 1 partnership/collaboration with one education opportunity

Time Frame: July 2026 – June 2028

Lead Persons: Stephanie Foster, Jessica Fisher, Barbara Allen

Action Steps - Increase awareness of culturally appropriate, accessible and inclusive behavioral health resources among patients in healthcare setting. - Promote educational materials and culturally appropriate, accessible and inclusive behavioral health resources to reduce stigma around assessing services. - Collaborate with schools, libraries, community centers and faith-based organizations to promote opportunities for youth to engage in open discussions around mental health.

Status Comment and Date of Review:

Across all priorities Workgroup: Community Health Worker Learning Collaborative (CHWLC) Co-Chairs: Amanda Toohey, Johns Hopkins Howard County Medical Center (JHHCMC); María José Candanoza, MPH, CCHW, Howard County Health Department LHIC Staff: Maribet Rivera-Brute, MPH Alignment: Aligns with all the SHIP Priorities

Goal 1. Create a centralized Community Health Worker (CHW) network across all organizations in Howard County to enhance collaboration, improve culturally appropriate, accessible, and inclusive resource sharing, and expand access to community-based health initiatives.

Objective 1.1. By June 2028, By June 2028, lead efforts to connect CHWs across the county to share resources and funding opportunities.

Measure: Baseline: 10 CHWs Target: 15 certified CHWs in Howard County 5 certified CHWs working at HCHD 8 of CHWs registered as LHIC members 4 quarterly CHW Learning Collaborative scheduled meetings

Time Frame: June 2025 – June 2028

Lead Persons: María José Candanoza, Amanda Toohey

Action Steps - Host quarterly CHW Learning Collaborative meetings to foster networking, share best practices and enhance professional development among CHWs across Howard County. - Expand outreach efforts and actively engage CHWs across Howard County by building strong outreach networks, fostering professional development opportunities and creating sustainable pathways for collaboration. - Increase awareness and accessibility of CHW certification by developing targeted outreach efforts, highlighting professional growth opportunities and showcasing the impact of CHWs on community health. - Actively promote funding opportunities to ensure long-term sustainability and growth of the CHW workforce in Howard County.

Status Comment and Date of Review: July – September 2025 updates - CHWLC Meetings have been held on: - March 2025 - Reviewed the CHWLC CHIP Action plan updates; divided into groups to develop a standard definition of a CHW and their expectations; took part in mindfulness training - June 2025 - Reviewed CHW roles within group member organizations; Presentation provided from partner The Healthy Church; analyzed survey on future topics to cover in Collaborative; discussed Continued Education for CHW’s/CHW program provider - September 2025 - Provided updates on Community Assets Profile (CAP) Project - Presented Photovoice project on the Elkridge community based on the CAP project - Shared Maryland Department of Health CHW Training List October – December 2025 updates - November 2025 - Hosted CHW Photovoice Exhibition for community members and partners - December 2025 - Planning on the next photovoice event highlighting Columbia – Long Reach community January – March 2026 updates - January 2026 - Hosted CHW Photovoice exhibition for community members highlighting the Long Reach community in Columbia. We had 22 people at the event. - Planning started to collaborate with The Healthy Church for a no-cost CHW program for high school students. - February 2026 - Planning and promotion on the next photovoice event highlighting the communities in Jessup and Savage, and the Harper’s choice community in Columbia. - CHW program for high school students started with The Healthy Church - March 2026 - Hosted CHW Photovoice Exhibition for community members highlighting the Jessup and Savage, and Harper’s Choice, Columbia communities. We had 72 people in total. - Planning started to host future Photovoice events in May and June 2026.

Objective 1.2. By June 2028, maintain and expand the CHWLC Workgroup membership to enhance workforce retention, foster professional development and ensure the long-term sustainability of CHW programs across the county.

Measure: Baseline: 0 partnership Target: 3 partnerships

Time Frame: September 2024 – June 2028

Lead Persons: María José Candanoza

Action Steps - Partner with local universities, healthcare providers, community-based organizations, and faith-based organizations to promote CHWLC through outreach events, digital communication channels and signage on site.

Status Comment and Date of Review: July – September 2025 updates - Strengthen partnership with The Healthy Church (Kirk Rookwood) - Scholarships offered to CHWLC members to take The Healthy Church’s CHW Training Program - Provided a training presentation about the Sexual and Reproductive Health services from Howard County Health Department, Family Health Services on September 22, 2025 - Provided training presentation about Doula services by Howard County Health Department on August 11, 2025 January – March 2026 updates - Provided training presentation during the March 12 CHWLC meeting on healthcare access options in Howard County

Goal 2. Elevate CHWs as trusted advocates in healthcare and social services by strengthening public awareness, expanding professional development and fostering partnerships that improve access and equity in community health.

Objective 2.1. By June 2028, develop best practices and expectations for CHWs to enhance professionalism, ensure consistency in service delivery and strengthen their role in bridging healthcare and social services.

Measure: Baseline: 0 training identified/provided Target: 3 training identified/provided

Time Frame: June 2026 – June 2028

Lead Persons: María José Candanoza, Amanda Toohey, Maribet Rivera-Brute

Action Steps - Highlight the unique ability of CHWs to bridge the gap between healthcare and social services by increasing awareness, strengthening collaboration and demonstrating their impact in improving health outcomes and social equity. - Develop a CHWs Continuing Education Unit (CEU) professional development opportunity based on Howard County specific needs. - Proactively seek and establish partnerships with diverse organizations to enhance CHW training opportunities, ensuring access to specialized knowledge, professional development and workforce sustainability.

Status Comment and Date of Review: July – September 2025 updates - Strengthen partnership with The Healthy Church (Kirk Rookwood) - Scholarships offered to CHWLC members to take The Healthy Church’s CHW Training Program - Discovered Maryland CHW Training Accreditation List - Working to include Howard County trainings to list October – December 2025 updates - November 2025 - Hosted CHW Photovoice Exhibition for community members and partners January – March 2026 - Hosted CHW Photovoice Exhibitions: January 22, March 5, and March 24 - Planning for professional development opportunity in collaboration with UMD Horowitz Center of HL - Start planning for National CHW Awareness Week 2026 - Start planning for CHW Photovoice featuring Owen Brown community in Columbia

Objective 2.2. By June 2028, establish a sustainable network connecting CHWs with community organizations, schools, local leaders and businesses by portraying the positive impact of CHWs in the community, developing structured referral mechanisms, fostering ongoing partnerships and increasing awareness of CHW contributions to healthcare and social services.

Measure: Baseline: 0 presentations to community partners 1 referral mechanism Target: 3 presentations to community partners 1 referral mechanism

Time Frame: June 2026 – June 2028

Lead Persons: María José Candanoza, Amanda Toohey

Action Steps - Highlight the impact and benefit of CHWs in the community. - Create Community Asset Profiles for specific Census Tracts in Howard County. - Collaborate with community partners and utilize CAREAPP to facilitate and monitor resident engagement in health education and social resources.

Status Comment and Date of Review: July – September 2025 - No presentations during this period. - 1 developed CAREAPP Referral Mechanism: - CAREAPP Referral Workflow for CHWs - Assess Needs - Identify individual's needs - Search for Services - Based on NA results or community member/individual need - Make the Referral - Select appropriate services - Track Referral Status - Follow-Up and feedback - 1/2 weeks follow up with community member to confirm service access, document outcomes and note any barriers or gaps in service. October – December 2025 updates - November 2025 - Hosted CHW Photovoice Exhibition for community members and partners

Objective 2.3. By June 2028, integrate CHWs into existing Howard County Health Department (HCHD) programs by developing structured workflows that enhance coordination, streamline service delivery and strengthen CHW engagement in healthcare and social services.

Measure: Baseline: 0 cross-sector partnership Target: 3 cross-sector partnerships

Time Frame: June 2026 - June 2028

Lead Person: María José Candanoza

Action Steps - Identify priority areas to promote health education opportunities by leveraging Community Assets Profile data. - Establish cross-sector partnerships with healthcare organizations, community-based organizations, businesses and social service agencies to promote culturally appropriate, accessible and inclusive health education resources.

Status Comment and Date of Review: July – September 2025 - Strengthen partnership with The Healthy Church (Kirk Rookwood) - Scholarships offered to CHWLC members to take the Healthy Church’s CHW Training Program January – March 2026 - Collaboration with The Healthy Church to provide CHW program for high school students

MPA = Mid-Point Assessment

ACS = American Community Survey (U.S. Census)

BRFSS = Maryland Behavioral Risk Factor Surveillance System

CHNA = Community Health Needs Assessment (Johns Hopkins Howard County Medical Center, 2022; 2025 in process)

GHF = Growing Healthy Families workgroup

HCHAS = Howard County Health Assessment Survey

MHSP = Healthy Minds and Suicide Prevention workgroup

MVA = Maryland Vital Statistics Administration

SHIP = Maryland State Health Improvement Plan (Building A Healthier Maryland, 2024)

YRBS = Youth Risk Behavior Survey